PROTECTION OF CIVILIANS

Scenario Base Exercise

Mission Planning Matrix

| CARANA – MISSION PLANNING MATRIX |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objective 1: Reestablishment of Peace and Security |  |  |  |  |  |  |
| Key Assumptions: 1 All parties (warring factions) abide by the Kalari Peace agreement. 2 All elements of UNAC are well established in their respective locations. 3 Free movement of UN personnel is secured. |  |  |  |  |  |  |
| Required Output | Activity | Timeframe | Success Criteria | Resources | Responsibility | Comment |
| 1. Keep warring factions are kept at a distance amongst them and not getting closer to each other | UN military contingents, observers and police will be deployed in areas including Lisbo, Akkabar, Maldosa, Lora, Perkes, visiting positions of all parties. | By September 22, all factions lay down their arms | No major confrontations would occur | Two infantry brigades deployed in each sector with 20 military observers | UNAC | Forces assets and efforts will be initially concentrated on more difficult situations in the Western and Southern parts of Carana where MPC and ICSC elements together with organized criminal groups will be the biggest challenge. |
| 2. Establish and maintain continuous liaison with the filed headquarters of all parties’ military forces | UN military observers and Grade 1 staff officers from sector headquarters will meet the warring factions in their respective areas | Immediately put into effective from September 22 to November 22 | All elements of warring factions maintain cease-fire and remain in their respective areas | Infantry Brigades and military observers | UNAC Force Commander Sector Headquarters |  |
| 3. Implement Voluntary DDR programme for all warring parties | 1. DDR cell will be established Joint UN 2.Joint technical committee will be formed to that end. 3.Ex-combattants will be reintegrated into the army provided that they meet standard criteria. | Immediately Immediately Within 6 months | 95% of weapons belonging to warring factions are desposed | UNAC UNAC UNDP | Force Commander DSRSG UNDP together with UNAC | DDR process will be fully integrated into planning of Objective 4 Priorities will also given to their rehabilitation into society meanwhile CDF will be restructured and reformed. |
| 4. Keep stable relations with warring factions on a number of issues | Continued negotiations with the warring factions | Launching immediately and continue until the end of the mandate | ---Maintenance of complete ceasefire ---No Violation of the Agreement ---Calm maintained | ---UN military personnel ---UN Police ---Military Observers | ---SRSG ---Force Commander ---Police Commissioner |  |
| 5.1 Establish the foundation for Force Projection | 1. Build deployment bases with appropriate C4I network for rest of deployment of military forces | M+120 | Complete the establishment of force receiving plan | UNCT | UNCT |  |
|  | 2. Secure the sealift/airlift installations to ensure the freedom of movement and logistics/supply requirment | M+60 | Project the appropriate armed troops to secure the Airport (Galasi & Corma), Seaport (Galasi & Cereni & Maldosa) for exclusive use of UN | UNCT/PDT | FC |  |
|  | 3. Establish ground transportation network between key stations | M+60 | Establish key logistics supply sites and ensure the free transit between each stations | UNAC | FC |  |
| 5.2 Establish Intelligence activities | 1. Conduct Air Patrol and reconnaissance | M+180 | Using helicopters and UNV for intelligence operations | UNAC | FC |  |
|  | 2. Conduct Ground Patrol and Reconnaissance | M+60 (M+120) | Collecting the intelligence and warning the uncontrolled armed group that UN patrol troops monitoring their activities | UNAC | FC |  |
| 5.3 Protect High Value Facilities | 1. Secure the Government Installations | M+60 (M+120) | Project security forces to designated important facilities to protect them | UNAC | FC Sector/Contingent Commanders |  |
|  | 2. Secure the UN Facilities | M+60 (M+120) | Project security forces to designated important facilities to protect them | UNAC | FC Sector/Contingent Commanders |  |
|  | 3. Protect assigned important facilities with vital infrastructure | M+60 (M+120) | Project security forces to designated important facilities to protect them | UNAC | FC Sector/Contingent Commanders |  |
| 5.4 Protection of Civilians | 1. Planning and preparing to action mission’s resources in all POC phases of response. 2. Execute military operations planned and approved. | Deployment + 30 | Civilians are protected from physical harm posed by armed groups. | UNAC DMS – Budget Carana PD Country Team Donations | FC Sector/Contingent Commanders |  |
| 5.5 Secure free access in Carana | De-mining in support of free access of Ground Patrol, Recon forces | To be determined | De-mining and secure the field for free access | UNAC | FC |  |
| 5.6 Enhance associated military operations | 1. Establish LNO with field headquarters of all parties’ military forces | Before main body arrives | All military operations are associated in prior, to prevent Blue-on-Blue incident | UNAC (Force Hq) | PDT/FC |  |
| Objective 2: Restoration of Good Governance |  |  |  |  |  |  |
| Key Assumptions: ---Kalari Peace Agreement will not be broken by either party |  |  |  |  |  |  |
| Required Output | Activity | Timeframe | Success Criteria | Resources | Responsibility | Comment |
| 1 Reestablish the national authority throughout the country | Administrative assistance to each ministry and local entities by dispatching administrative advisers in different areas | Immediately | Establishment of functional administration | Funding by UN agencies and international donors | UNAC Civil Affairs Office UNDP | Appropriate coordination is necessary amongst donors and UN agencies |
| 2 Create a functional legal / judicial systems | 1. Assessing Carana Criminal Justice System 2. Technical assistance for establishment of a national legal framework 3. Recruit and training of judges, prosecutors, other needed officials in judicial system 4. Establishment of several correctional institutions. | Within 3 months Within 6 months Within 9 months Within 12 months | 1. Adoption of a national legal framework 2. Successful functioning of judicial systems 3. Public Prosecutor and its office, Court and judges, Corrections and its officers, organization are reformed and their capacity is developed. | Funding by UNDP, UNODC, UNAFEI and international donors | Carana GNR supported by Judiciary and Corrections Office in UNAC | Coordination among donors is critical Competent existing officers are considered for continuing for development training session, |
| 3 Establish National Counter Corruption Agency/Commission | 1. Adoption of necessary laws & regulations 2. Establish organization with necessary: Personnel/staff Facility | Within 6 months Within 1 year | National Counter Corruption Commission and its office are established | Funding by UNDP, UNODC and UNAFEI | UNAC and other CJ Experts |  |
| 4 Nurturing an environment conducive to holding elections | 1. Raising awareness amongst the people on electoral system 2. Providing support for formation of electoral committee 3. Other necessary preparations for elections | Start immediately and complete by June 2007 Within 6 months Within 12 months | Holding of elections at an appropriate timing | Funding by UN DPA and UNDP in addition to international donors | Electoral Assistance Team dispatched by DPA | Targeting at holding elections as soon as a relatively stable environment is secured, preferably toward the end of 12 months. However, timing of national elections is to be determined according to the progress in other areas of the mission |
| Objective 3: Reestablishment of Rule of Laws including Human Rights |  |  |  |  |  |  |
| Key Assumptions: 1. Agreement on the International Police Task Force is in place (Sovereignty & Legitimacy (jurisdiction) Issue); 2. Criminal Code or Interim Criminal Laws exists. 3. Government of National Reconciliation give full and unlimited access to the current police force. 4. Supporting and relevant laws are already in place. 5. Local Resource Person, Police Experts and necessary Contact Person are available to provide assistance and involvements. 6. UNAC activities progresses as per the time-lines given in the Security Council Resolution 1544 |  |  |  |  |  |  |
| Required Output | Activity | Timeframe | Success Criteria | Resources | Responsibility | Comment |
| 1 Set up the structure and system for UN Police Administration and Operation | Establish Rules & Regulations Coordinating with Carana PD Contracting with relevant unit Budgeting Allocation | Within the 1st week and onward | UN Police HQ and Regional HQ, Police Station and Sub-stations are established. Functional & operational UN Police The Command, Control, Communication and Information Center (C3I) system & facilities is established and functioning | DMS – Budget Carana PD Country Team Donation | UN Police Commission UNODC and Country Team Donor Countries | Use what is provided. Repair what is broken. Build/acquire what is needed. Maintenance and continuous develop on what we have. |
| 2 Provide police service through out the country. | Staffing UN Police HQ Deploying UN Police to staff Regional HQ, Stations and Sub-stations | After the 1st week and onward | All police units at every level are staff (at least to the minimum operable level) | DMS – Budget Carana PD Country Team Donations | UN Police Commission Regional Com. Station Chief UNODC and Country Team Donor Countries | Use what is provided. Repair what is broken. Build/acquire what is needed. Maintenance and continuous develop on what we have. |
| 3 Assess Carana PD | Assess CPD’s current capacity, capability and needs | Within 1 month | Assessment Report: (Where we are; what is needed to be where we want to be) | DMS - Budget | Assessment Team | Assistance from Local Resource persons |
| 4 Build Internationally acceptable police officers | Reform Police Personnel System: - Recruiting & Selection - Training - Salary, Benefits, Rewarding - Discipline - Termination | Within 3 month Within 6 month | 100 Police Officers with basic skills and professionalism | DMS – Budget UNODC and Country Team Donor Countries | Carana PD – Main Training Team – Sub Advisory Group – Sub | Competent existing police officer will be considered for continuing with the Force (on a case by case basis) and given priority for a short.(1 mth) separate-retaining course |
| 5 Provide necessary Tools, Equipments and Vehicles | Budgeting Allocation Logistics | After 1 month onward | New tools, Equipments and Vehicle | Carana PD Country Team Donation | Carana PD UNODC and Country Team Donor Countries | Capacity Bldg. Repair what’s broke. Maintenance what’s having.. Find/Get what’s needed. |
| 6 Provide necessary facilities including - Station house - Holding Cells | Budgeting Allocation Coordinating/ Contracting with relevant unit | After 1 month onward | Functional & operational police facilities | Carana PD Country Team Donation | Carana PD UNODC and Country Team Donor Countries | Capacity Bldg. Repair what break. Maintenance what have Build what need. |
| 7 Reform and Restructure Carana PD | Assess and Evaluate the Org. Structure of Carana PD Re-engineer the Police organization structure and system | 6 months 1 year | Carana PD is restructured of its organization & work system | DMS – Budget Country Team Donation | Assessment Team Resource Person Carana Intrm. Government Advisory Group Police Experts Outside Experts | Institutional Capacity Bldg. Initiative |
| 8 Reform and Restructure Carana Defense Forces (CDF) composed of 10,000 military personnel | 1. Establishing Military Academy 2. Training of former combatants at Recruit Training Centres 3. Reconstructionn of Camps, Bases, and other Installations | By August 2007 | Army, Navy and Air Force Chiefs take over the stock of the forces and chain of command established | 1. Personnel from existing defense forces and rebel groups 2. Military hardwares from friendly states | UN Country Team of UNAC Donor Agencies Friendly States GNR Peace Building Commission | Restructuring of CDF will be progressing simultaneously with other tasks and activities of UNAC |
| 9 Strengthening human rights, especially those of women and children | Strengthen law enforcement with a particular attention to women and children | Immediately |  | UNDP OCHA | Police Commissioner |  |
| Objective 4: Creating a sustainable environment for the people of Carana |  |  |  |  |  |  |
| Key Assumptions: ---Provision of humanitarian assistance to all IDP and refugee camps is sufficiently secured. ---Donors and other stakeholders in Carana continue to commit to a sustainable development of the country. |  |  |  |  |  |  |
| Required Output | Activity | Timeframe | Success Criteria | Resources | Responsibility | Comment |
| 1. Improve living condition of 11 IDP and refugee camps in accordance with UN standards through humanitarian assistance | 1. UN country team and representatives of donors visit IDP and refugee camps for a fact-finding mission for needs assessment 2.Joint Coordination Committee is established for better coordination amongst stakeholders 3. Initial start-up for emergency relief for a selected locations of IDP and refugees camps 4. Engagement of local and international media on the suffering of IDPs and refugees | Immediately Within one month Within one month | Situation in camps and basic needs for their living are identified properly Better coordination amongst UN agencies and donors Sufficient coverage in the media on the issue | Funding by UNDP, WFP UNHCR, WHO and other UN agencies ICRC/IFRC International donors NGOs CERF may be utilized accordingly | DSRSG and UN country team | CAP should be introduced in due course Security is secured for the transport of humanitarian aids |
| 2. Render support for the capacity building of IDPs and refugees in preparation for their return to home | 1. Capacity-building programme for IDPs and refugees 2. Assistance to their relocation | Within 3 months Within 12 months | IDPs and refugees acquire sufficient capacity to reestablish their life | Funding by UNHCR, IOM, UNDP and other UN Agencies and donors | UN Country Team UNHCR, IOM, UNDP and other UN Agencies | Security should be established before their return to homes |
| 3. Launch initial preparation for recovery and sustainable development | 1. Establishment of joint coordination committee to better prepare for peace-building 2. Active engagement of donors and other stakeholders for the recovery of Carana through assisting in holding of donor conference 3. Launching quick impact projects | Within 3 months Within 3 months Within 3 months | Sufficient amount of assistance is pledged and committed by international donors | Funding by UNDP and other UN agencies World Bank International donors | UN Country Team UNDP and other UN agencies World Bank International donors |  |
| 4 Secure funding for long-term sustainable development including also better management of natural resources | 1 Dispatch of experts in areas of mining to assist Carana GNR for better management of natural resources 2 Design a new strategy for sustainable development of Carana 3 Launching of donor conference based on a new strategy | Within 3 months |  | Funding by World Bank | World Bank + UN Country Team as necessary | World Bank will take lead on sustainable development including management of natural resources |
| Other measures necessary for Mission Support: |  |  |  |  |  |  |
| Key Assumptions: negotiation with TCC/PCC for the conclusion of MOU (List of support item) is in progress. |  |  |  |  |  |  |
| Required Output | Activity | Timeframe | Success Criteria | Resources | Responsibility | Comment |
| 1 Budget approval | Submit the budget request | ASAP | Request has been approved in order to execute Operation plan |  | DMS |  |
| 2 Conclude MOU with TCC/PCC | Negotiate the logistics plan and supply items with TCC/PCC | ASAP | Complete coordination with TCC/PCC, determining the detail logistics/support items and reinvestment |  | SRSG/DMS/CT |  |
| 3 Establish robust logistics mechanism | 1. provide sealift/airlift capability for military operations and logistics requirement 2. Provide land transportation for military logistics/supply requirement, and humanitarian assistance | Within 6 months after projection started Within 6 months after projection started | Complete contract with commercial company to schedule the logistics sealift/airlift, or negotiate with TCC to provide strategic transportation Establish ground transportation for distribution of supply items | Charter (TCC) UNAC | DMS DMS |  |